## project schedule crea
Project Schedule Creation
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
To-do
Name | Due Date | Priority | Notes | Files | Timeline - Start | Timeline - End | Last updated | Dependency
Task 1: Requirement Gathering | 2024-04-05 | Low |  | https://team962526.monday.com/protected_static/22852320/resources/43303752/file.png | 2024-04-01 | 2024-04-05 | Shubnam Pillay Apr 15, 2024 11:18 AM
UI/UX Design, Backend Development |  | Medium |  |  |  |  | Shubnam Pillay Apr 15, 2024 11:48 AM
Task 2: UI/UX Design | 2024-04-10 | High |  |  | 2024-04-01 | 2024-04-10 | Shubnam Pillay Apr 15, 2024 11:19 AM | Task 1: Requirement Gathering
Task 3: Backend Development | 2024-04-20 | Medium | Other |  | 2024-04-01 | 2024-04-20 | Shubnam Pillay Apr 15, 2024 11:21 AM | Task 1: Requirement Gathering
Task 4: Database Setup | 2024-04-21 | High | Other |  | 2024-04-01 | 2024-04-15 | Shubnam Pillay Apr 15, 2024 11:22 AM | Task 3: Backend Development
Task 5:Frontend Development | 2024-04-15 | Medium | Other |  | 2024-04-01 | 2024-04-15 | Shubnam Pillay Apr 15, 2024 11:23 AM | UI/UX Design, Backend Development
Task 6: Integration Testing | 2024-04-22 | High | Other |  | 2024-04-01 | 2024-04-10 | Shubnam Pillay Apr 15, 2024 11:24 AM | Task 3: Backend Development, Task 4: Database Setup, Task 5:Frontend Development
Deplo |  | High |  |  |  |  | Shubnam Pillay Apr 15, 2024 11:48 AM
Task 7: User Acceptance Testing (UAT) | 2024-04-23 | High | Other |  | 2024-04-01 | 2024-04-10 | Shubnam Pillay Apr 15, 2024 11:25 AM | Task 6: Integration Testing
Task 8:Bug Fixing and Optimization | 2024-04-24 | Medium | Other |  | 2024-04-01 | 2024-04-10 | Shubnam Pillay Apr 15, 2024 11:27 AM | Task 7: User Acceptance Testing (UAT)
Task 9:Deployment Planning | 2024-04-05 | Medium | Other |  | 2024-04-01 | 2024-04-05 | Shubnam Pillay Apr 15, 2024 11:28 AM | Task 7: User Acceptance Testing (UAT)
Task 10: Deployment | 2024-04-05 | High |  |  | 2024-04-01 | 2024-04-05 | Shubnam Pillay Apr 15, 2024 11:29 AM | Task 9:Deployment Planning
| 2024-04-05 to 2024-04-24 |  |  |  | 2024-04-01 | 2024-04-20
Completed
Name | Due Date | Priority | Notes | Files | Timeline - Start | Timeline - End | Last updated | Dependency
Task 1: Requirement Gathering | 2024-04-05 | High | Completed |  | 2024-04-01 | 2024-04-05 | Shubnam Pillay Apr 15, 2024 11:49 AM
| 2024-04-05 |  |  |  | 2024-04-01 | 2024-04-05
Resource Allocation
Name | Due Date | Priority | Notes | Files | Timeline - Start | Timeline - End | Last updated | Dependency
Product owner/client |  | High | Sitting outside of the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:33 AM
UX/UI Designer: 1 Resource |  | High | Sitting outside of the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:34 AM
Developer 1: Full Stack Senior Developer |  | High | Sitting in the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:36 AM
Developer 2: Full Stack Intermediate Developer |  | High | Sitting in the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:36 AM
Developer 3: Junior Backend Developer |  | High | Sitting in the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:37 AM
Developer 4:Junior Frontend Developer |  | Medium | Sitting in the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:37 AM
Tester 1:Test Analyst (Manual) |  | High | Sitting in the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:38 AM
Tester 2:Automation Tester |  | Medium | Sitting in the team |  |  |  | Shubnam Pillay Apr 15, 2024 11:38 AM